## Traceability
Requirement | Source | Implemented | Implementation | Tests | Result | Status | Evidence | Action
R1 | CVT-EST-001 Rev C §5 R1 (§3) | Y | kalman_update.m line 1: function X = kalman_update(Z, model) | T1 | PASS | VERIFIED | T1 calls X = kalman_update(Z, model) and uses the result.
R2 | CVT-EST-001 Rev C §5 R2 (§3) | Y | X = zeros(N, n); X(k, :) = x' per step, k = 1..N | T1, T3 | PASS | VERIFIED | T1 asserts size(X) == [rows(Z), 4]; T3 compares X(:,1:2) with Z row by row, so order is exercised (loosely).
R3 | CVT-EST-001 Rev C §5 R3 (§4) | Y | x = model.x0; P = model.P0; predict x = F*x, P = F*P*F' + Q; update K = (P*H')/S, x = x + K*y, P = (I - K*H)*P | T3 | PASS | PARTIAL | T3 only bounds ¦X(:,1:2) - Z¦ < 5.0, which a badly wrong recursion could still pass, and every test uses x0 = 0, P0 = I, so initialization from model.x0/model.P0 is never exercised. No comparison against a reference computation. | Add a test with non-default x0/P0 and a tight comparison against an independent evaluation of §4.
R4 | CVT-EST-001 Rev C §5 R4 | Y | Pure function: no globals, files, or randomness | T2 | PASS | VERIFIED | T2 asserts isequal(X, kalman_update(Z, model)).
R5 | CVT-EST-001 Rev C §5 R5 | Y | test_kalman.m (runs on test_vectors.csv) | T1, T2, T3 | PASS (test_results.txt, 2026-03-10, v2.2.0) | VERIFIED | Suite is runnable and exercises R1-R4 on test_vectors.csv; 3 passed, 0 failed. Its R3 coverage is partial (see R3).
R6 | CVT-EST-001 Rev C §5 R6 | N | None: no isfinite/validity check on Z; a NaN row flows through y = z - H*x into x and P | none | - | NOT_IMPLEMENTED | No input validation in kalman_update.m and no test with NaN/Inf or malformed measurements. | Implement rejection and reporting of non-finite or malformed measurements, and add tests for it.